## Report
Instructions: |  | Delete example data and adjust files as needed for project requirements.
QC sheet for: |  | HMA Asphalt Content and Compaction
Project #: | 495Z7 | Project Name: | Haines Highway Widening
Mix Design No. |  | 12C-129 |  | Mix Type: | Asphalt Concrete Type IIA
|  |  | Asphalt Cement Content Control | [8 empty] | Compaction Control
Test # | Sample Date | Sampled by | Sample Location | Sample Method | Lab No. | Truck # | Date Reported | Tested by | Test # | Sample Date | Sampled by | Sample Location | Sample Method | Lab No. | Date Reported | Tested by
1 | 2012-02-08 | B. Jones | Windrow | ATM 403 | 15682 | 167 | 2012-02-10 | R. Simmons | 1 | 2012-02-07 | J. Doe | Sta. 125+30, 10' Rt. | ATM 413 | 16520 | 2012-02-09 | R. Simmons
2 | 2012-02-10 | B. Jones | Windrow | ATM 403 | 15684 | 459 | 2012-02-11 | R. Simmons | 2 | 2012-02-09 | J. Doe | Sta. 135+50, 6' Rt. | ATM 413 | 16522 | 2012-02-11 | R. Simmons
3 | 2012-02-15 | B. Jones | Windrow | ATM 403 | 15686 | 621 | 2012-02-16 | R. Simmons | 3 | 2012-02-14 | J. Doe | Sta 148+90, 7' Lt. | ATM 413 | 16524 | 2012-02-15 | R. Simmons
4 | 2012-02-20 | B. Jones | Windrow | ATM 403 | 15688 | 734 | 2012-02-21 | R. Simmons | 4 | 2012-02-19 | J. Doe | Sta 155+20, 5' Rt. | ATM 413 | 16526 | 2012-02-20 | R. Simmons
5 | 2012-02-27 | B. Jones | Windrow | ATM 403 | 15690 | 216 | 2012-02-28 | R. Simmons | 5 | 2012-02-26 | J. Doe | Sta. 173+35, 5' Lt. | ATM 413 | 16528 | 2012-02-27 | R. Simmons
6 | 2012-02-28 | B. Jones | Windrow | ATM 403 | 15692 | 167 | 2012-02-29 | R. Simmons | 6 | 2012-02-27 | J. Doe | Sta 185+60, 9' Rt. | ATM 413 | 16530 | 2012-02-28 | R. Simmons
7 | 2012-02-29 | B. Jones | Windrow | ATM 403 | 15694 | 734 | 2012-03-01 | R. Simmons | 7 | 2012-02-28 | J. Doe | Sta 196+10, 10' Lt. | ATM 413 | 16532 | 2012-02-29 | R. Simmons
8 | 2012-03-01 | B. Jones | Windrow | ATM 403 | 15696 | 459 | 2012-03-02 | R. Simmons | 8 | 2012-02-29 | J. Doe | Sta 204+80, 5' Lt. | ATM 413 | 16534 | 2012-03-01 | R. Simmons
9 | 2012-03-02 | B. Jones | Windrow | ATM 403 | 15698 | 621 | 2012-03-03 | R. Simmons | 9 | 2012-03-01 | J. Doe | Sta. 215+50, 3' Rt. | ATM 413 | 16536 | 2012-03-02 | R. Simmons
10 | 2012-03-05 | B. Jones | Windrow | ATM 403 | 15700 | 216 | 2012-03-06 | R. Simmons | 10 | 2012-03-04 | J. Doe | Sta. 235+50, 6' Rt. | ATM 413 | 16538 | 2012-03-05 | R. Simmons
11 | 2012-03-06 | B. Jones | Windrow | ATM 403 | 15702 | 621 | 2012-03-07 | R. Simmons | 11 | 2012-03-05 | J. Doe | Sta 248+90, 7' Lt. | ATM 413 | 16540 | 2012-03-06 | R. Simmons
12 | 2012-03-07 | B. Jones | Windrow | ATM 403 | 15704 | 947 | 2012-03-08 | R. Simmons | 12 | 2012-03-06 | J. Doe | Sta 255+20, 5' Rt. | ATM 413 | 16542 | 2012-03-07 | R. Simmons
13 | 2012-03-08 | B. Jones | Windrow | ATM 403 | 15706 | 216 | 2012-03-09 | R. Simmons | 13 | 2012-03-07 | J. Doe | Sta. 273+35, 5' Lt. | ATM 413 | 16544 | 2012-03-08 | R. Simmons
14 | 2012-03-09 | B. Jones | Windrow | ATM 403 | 15708 | 459 | 2012-03-10 | R. Simmons | 14 | 2012-03-08 | J. Doe | Sta 285+60, 9' Rt. | ATM 413 | 16546 | 2012-03-09 | R. Simmons
15 | 2012-03-10 | B. Jones | Windrow | ATM 403 | 15710 | 734 | 2012-03-11 | R. Simmons | 15 | 2012-03-09 | J. Doe | Sta 296+10, 10' Lt. | ATM 413 | 16548 | 2012-03-10 | R. Simmons
16 | 2012-03-12 | B. Jones | Windrow | ATM 403 | 15712 | 167 | 2012-03-13 | R. Simmons | 16 | 2012-03-11 | J. Doe | Sta 304+80, 5' Lt. | ATM 413 | 16550 | 2012-03-12 | R. Simmons
17 | 2012-03-13 | B. Jones | Windrow | ATM 403 | 15714 | 621 | 2012-03-14 | R. Simmons | 17 | 2012-03-12 | J. Doe | Sta. 315+50, 3' Rt. | ATM 413 | 16552 | 2012-03-13 | R. Simmons
18 | 2012-03-14 | B. Jones | Windrow | ATM 403 | 15716 | 459 | 2012-03-15 | R. Simmons | 18 | 2012-03-13 | J. Doe | Sta. 335+50, 6' Rt. | ATM 413 | 16554 | 2012-03-14 | R. Simmons
19 | 2012-03-15 | B. Jones | Windrow | ATM 403 | 15718 | 459 | 2012-03-16 | R. Simmons | 19 | 2012-03-14 | J. Doe | Sta 348+90, 7' Lt. | ATM 413 | 16556 | 2012-03-15 | R. Simmons
20 | 2012-03-16 | B. Jones | Windrow | ATM 403 | 15720 | 734 | 2012-03-17 | R. Simmons | 20 | 2012-03-15 | J. Doe | Sta 355+20, 5' Rt. | ATM 413 | 16558 | 2012-03-16 | R. Simmons
21 | 2012-03-17 | B. Jones | Windrow | ATM 403 | 15722 | 621 | 2012-03-18 | R. Simmons | 21 | 2012-03-16 | J. Doe | Sta. 373+35, 5' Lt. | ATM 413 | 16560 | 2012-03-17 | R. Simmons
22 | 2012-03-19 | B. Jones | Windrow | ATM 403 | 15724 | 947 | 2012-03-20 | R. Simmons | 22 | 2012-03-18 | J. Doe | Sta 385+60, 9' Rt. | ATM 413 | 16562 | 2012-03-19 | R. Simmons
23 | 2012-03-20 | B. Jones | Windrow | ATM 403 | 15726 | 621 | 2012-03-21 | R. Simmons | 23 | 2012-03-19 | J. Doe | Sta 396+10, 10' Lt. | ATM 413 | 16564 | 2012-03-20 | R. Simmons
24 | [8 empty] | 24 | 2012-03-22 | J. Doe | Sta 409+10, 8' Rt. | ATM 413 | 16566 | 2012-03-23 | R. Simmons
25 | [8 empty] | 25
26 | [8 empty] | 26
27 | [8 empty] | 27
28 | [8 empty] | 28
29 | [8 empty] | 29
30 | [8 empty] | 30
31 | [8 empty] | 31
32 | [8 empty] | 32
33 | [8 empty] | 33
34 | [8 empty] | 34
35 | [8 empty] | 35
36 | [8 empty] | 36
37 | [8 empty] | 37
38 | [8 empty] | 38
39 | [8 empty] | 39
40 | [8 empty] | 40
Formulas:
Date Reported = [Sample Date]+2
Sample Date = [Sample Date]-1

## Input
Data for: | HMA Asphalt Content and Compaction | [5 empty] | Project: | Haines Highway Widening
INPUT BY: | A.D. Charlie | [5 empty] | Material Tested: | HMA Mix and Cores
CHECKED BY: |  | B. Johnson, P.A. |  |  |  |  | Mix Design No.: | 12C-132
| Asphalt Cement Content Control Data | [5 empty] | Compaction Control Data
Test # | AC Sample Date | AC Content Lab # | AC Content Test Method | Asphalt Cement Content | Compaction Sample Date | Compaction Lab # | Density Test Method | Tested Density (Gmb) | Density Standard (Gmm) | % Compaction | Test #
1 | 2012-02-08 | 15682 | ATM 406 | 5.2 | 2012-02-07 | 16520 | ATM 410 | 2.2725 | 2.4567 | 92.5 | 1
2 | 2012-02-10 | 15684 | ATM 406 | 5.2 | 2012-02-09 | 16522 | ATM 410 | 2.297 | 2.4567 | 93.5 | 2
3 | 2012-02-15 | 15686 | ATM 406 | 4.8 | 2012-02-14 | 16524 | ATM 410 | 2.3364 | 2.4567 | 95.1 | 3
4 | 2012-02-20 | 15688 | ATM 406 | 4.7 | 2012-02-19 | 16526 | ATM 410 | 2.1939 | 2.4567 | 89.3 | 4
5 | 2012-02-27 | 15690 | ATM 406 | 4.7 | 2012-02-26 | 16528 | ATM 410 | 2.2479 | 2.4567 | 91.5 | 5
6 | 2012-02-28 | 15692 | ATM 406 | 4.7 | 2012-02-27 | 16530 | ATM 410 | 2.1767 | 2.4567 | 88.6 | 6
7 | 2012-02-29 | 15694 | ATM 406 | 5.1 | 2012-02-28 | 16532 | ATM 410 | 2.2405 | 2.4567 | 91.2 | 7
8 | 2012-03-01 | 15696 | ATM 406 | 4.8 | 2012-02-29 | 16534 | ATM 410 | 2.2848 | 2.4567 | 93 | 8
9 | 2012-03-02 | 15698 | ATM 406 | 5.1 | 2012-03-01 | 16536 | ATM 410 | 2.2479 | 2.4567 | 91.5 | 9
10 | 2012-03-05 | 15700 | ATM 406 | 5.2 | 2012-03-04 | 16538 | ATM 410 | 2.2872 | 2.4567 | 93.1 | 10
11 | 2012-03-06 | 15702 | ATM 406 | 5.3 | 2012-03-05 | 16540 | ATM 410 | 2.2735 | 2.4712 | 92 | 11
12 | 2012-03-07 | 15704 | ATM 406 | 5.4 | 2012-03-06 | 16542 | ATM 410 | 2.3847 | 2.4712 | 96.5 | 12
13 | 2012-03-08 | 15706 | ATM 406 | 5.5 | 2012-03-07 | 16544 | ATM 410 | 2.3921 | 2.4712 | 96.8 | 13
14 | 2012-03-09 | 15708 | ATM 406 | 5.6 | 2012-03-08 | 16546 | ATM 410 | 2.3921 | 2.4712 | 96.8 | 14
15 | 2012-03-10 | 15710 | ATM 406 | 5.4 | 2012-03-09 | 16548 | ATM 410 | 2.3155 | 2.4712 | 93.7 | 15
16 | 2012-03-12 | 15712 | ATM 406 | 5.3 | 2012-03-11 | 16550 | ATM 410 | 2.3847 | 2.4712 | 96.5 | 16
17 | 2012-03-13 | 15714 | ATM 406 | 5.1 | 2012-03-12 | 16552 | ATM 410 | 2.2982 | 2.4712 | 93 | 17
18 | 2012-03-14 | 15716 | ATM 406 | 5.4 | 2012-03-13 | 16554 | ATM 410 | 2.3427 | 2.4712 | 94.8 | 18
19 | 2012-03-15 | 15718 | ATM 406 | 5.3 | 2012-03-14 | 16556 | ATM 410 | 2.4193 | 2.4712 | 97.9 | 19
20 | 2012-03-16 | 15720 | ATM 406 | 5.6 | 2012-03-15 | 16558 | ATM 410 | 2.3402 | 2.4712 | 94.7 | 20
21 | 2012-03-17 | 15722 | ATM 406 | 5.4 | 2012-03-16 | 16560 | ATM 410 | 2.3588 | 2.4647 | 95.7 | 21
22 | 2012-03-19 | 15724 | ATM 406 | 5.3 | 2012-03-18 | 16562 | ATM 410 | 2.2873 | 2.4647 | 92.8 | 22
23 | 2012-03-20 | 15726 | ATM 406 | 5.3 | 2012-03-19 | 16564 | ATM 410 | 2.3908 | 2.4647 | 97 | 23
24 |  | 0 |  |  | 2012-03-22 | 16566 | ATM 410 | 2.4007 | 2.4647 | 97.4 | 24
25 |  | 0 |  |  |  | 0 |  |  |  |  | 25
26 |  | 0 |  |  |  | 0 |  |  |  |  | 26
27 |  | 0 |  |  |  | 0 |  |  |  |  | 27
28 |  | 0 |  |  |  | 0 |  |  |  |  | 28
29 |  | 0 |  |  |  | 0 |  |  |  |  | 29
30 |  | 0 |  |  |  | 0 |  |  |  |  | 30
31 |  | 0 |  |  |  | 0 |  |  |  |  | 31
32 |  | 0 |  |  |  | 0 |  |  |  |  | 32
33 |  | 0 |  |  |  | 0 |  |  |  |  | 33
34 |  | 0 |  |  |  | 0 |  |  |  |  | 34
35 |  | 0 |  |  |  | 0 |  |  |  |  | 35
36 |  | 0 |  |  |  | 0 |  |  |  |  | 36
37 |  | 0 |  |  |  | 0 |  |  |  |  | 37
38 |  | 0 |  |  |  | 0 |  |  |  |  | 38
39 |  | 0 |  |  |  | 0 |  |  |  |  | 39
40 |  | 0 |  |  |  | 0 |  |  |  |  | 40
|  | Upper Spec. Limit: |  | 5.4 |  |  |  | Upper Spec. Limit: |  | 98
|  | Mean of Tests: |  | 5.1913 |  |  |  | Mean of Tests: |  | 93.9542
|  | Lower Spec. Limit |  | 4.6 |  |  |  | Lower Spec. Limit |  | 92
|  | Mix Design Target: |  | 5

## %AC
Tests for: |  | Asphalt % |  | Test of: | [8 empty] | HMA Mix
Test Method: |  | ATM 406 |  | Test Units: | [8 empty] | %
Chart by: |  | A.D. Charlie |  | Project #: | [8 empty] | 495Z7
Contractor: |  | Hi-Ball Construction |  | Item #: | [8 empty] | 401(2)
|  |  |  | Checked by: | [8 empty] | B. Johnson, P.A.
S. Date | Test No. | Test Result* | Range* | Notes | Test UCL | U. Spec | Test C/L | L. Spec. | Test LCL | Range C/L | Range UCL | Range LCL
2012-02-08 | 1 | 5.2 |  |  | 5.6145 | 5.4 | 5.1913 | 4.6 | 4.7681 | 0.15909 | 0.52023 | 0 | Individual Tests | Data
2012-02-10 | 2 | 5.2 | 0 |  | 5.6145 | 5.4 | 5.1913 | 4.6 | 4.7681 | 0.15909 | 0.52023 | 0 | Average (C/L) | 5.1913
2012-02-15 | 3 | 4.8 | 0.4 |  | 5.6145 | 5.4 | 5.1913 | 4.6 | 4.7681 | 0.15909 | 0.52023 | 0 | JMF Target
2012-02-20 | 4 | 4.7 | 0.1 | Adj-P1 | 5.6145 | 5.4 | 5.1913 | 4.6 | 4.7681 | 0.15909 | 0.52023 | 0
2012-02-27 | 5 | 4.7 | 0 | Adj-P1 | 5.6145 | 5.4 | 5.1913 | 4.6 | 4.7681 | 0.15909 | 0.52023 | 0 | Upper Control Limit | 5.6145
2012-02-28 | 6 | 4.7 | 0 | Adj-P1 | 5.6145 | 5.4 | 5.1913 | 4.6 | 4.7681 | 0.15909 | 0.52023 | 0 | Upper Spec. Limit | 5.4
2012-02-29 | 7 | 5.1 | 0.4 |  | 5.6145 | 5.4 | 5.1913 | 4.6 | 4.7681 | 0.15909 | 0.52023 | 0 | Lower Spec. Limit | 4.6
2012-03-01 | 8 | 4.8 | 0.3 |  | 5.6145 | 5.4 | 5.1913 | 4.6 | 4.7681 | 0.15909 | 0.52023 | 0 | Lower Control Limit | 4.7681
2012-03-02 | 9 | 5.1 | 0.3 |  | 5.6145 | 5.4 | 5.1913 | 4.6 | 4.7681 | 0.15909 | 0.52023 | 0
2012-03-05 | 10 | 5.2 | 0.1 |  | 5.6145 | 5.4 | 5.1913 | 4.6 | 4.7681 | 0.15909 | 0.52023 | 0
2012-03-06 | 11 | 5.3 | 0.1 |  | 5.6145 | 5.4 | 5.1913 | 4.6 | 4.7681 | 0.15909 | 0.52023 | 0
2012-03-07 | 12 | 5.4 | 0.1 |  | 5.6145 | 5.4 | 5.1913 | 4.6 | 4.7681 | 0.15909 | 0.52023 | 0
2012-03-08 | 13 | 5.5 | 0.1 | Adj-P3 | 5.6145 | 5.4 | 5.1913 | 4.6 | 4.7681 | 0.15909 | 0.52023 | 0
2012-03-09 | 14 | 5.6 | 0.1 | Adj-P3 | 5.6145 | 5.4 | 5.1913 | 4.6 | 4.7681 | 0.15909 | 0.52023 | 0
2012-03-10 | 15 | 5.4 | 0.2 | Adj-P3 | 5.6145 | 5.4 | 5.1913 | 4.6 | 4.7681 | 0.15909 | 0.52023 | 0
2012-03-12 | 16 | 5.3 | 0.1 |  | 5.6145 | 5.4 | 5.1913 | 4.6 | 4.7681 | 0.15909 | 0.52023 | 0
2012-03-13 | 17 | 5.1 | 0.2 |  | 5.6145 | 5.4 | 5.1913 | 4.6 | 4.7681 | 0.15909 | 0.52023 | 0
2012-03-14 | 18 | 5.4 | 0.3 |  | 5.6145 | 5.4 | 5.1913 | 4.6 | 4.7681 | 0.15909 | 0.52023 | 0
2012-03-15 | 19 | 5.3 | 0.1 |  | 5.6145 | 5.4 | 5.1913 | 4.6 | 4.7681 | 0.15909 | 0.52023 | 0
2012-03-16 | 20 | 5.6 | 0.3 |  | 5.6145 | 5.4 | 5.1913 | 4.6 | 4.7681 | 0.15909 | 0.52023 | 0 | Test Ranges | Chart data
2012-03-17 | 21 | 5.4 | 0.2 |  | 5.6145 | 5.4 | 5.1913 | 4.6 | 4.7681 | 0.15909 | 0.52023 | 0 | Average (C/L) | 0.15909
2012-03-19 | 22 | 5.3 | 0.1 |  | 5.6145 | 5.4 | 5.1913 | 4.6 | 4.7681 | 0.15909 | 0.52023 | 0
2012-03-20 | 23 | 5.3 | 0 |  | 5.6145 | 5.4 | 5.1913 | 4.6 | 4.7681 | 0.15909 | 0.52023 | 0
| 24 | No Data | N/A |  | 5.6145 | 5.4 | 5.1913 | 4.6 | 4.7681 | 0.15909 | 0.52023 | 0 | Upper Control Limit | 0.52023
| 25 | No Data | N/A |  | 5.6145 | 5.4 | 5.1913 | 4.6 | 4.7681 | 0.15909 | 0.52023 | 0 | Lower Control Limit | 0
| 26 | No Data | N/A |  | 5.6145 | 5.4 | 5.1913 | 4.6 | 4.7681 | 0.15909 | 0.52023 | 0
| 27 | No Data | N/A |  | 5.6145 | 5.4 | 5.1913 | 4.6 | 4.7681 | 0.15909 | 0.52023 | 0
| 28 | No Data | N/A |  | 5.6145 | 5.4 | 5.1913 | 4.6 | 4.7681 | 0.15909 | 0.52023 | 0
| 29 | No Data | N/A |  | 5.6145 | 5.4 | 5.1913 | 4.6 | 4.7681 | 0.15909 | 0.52023 | 0
| 30 | No Data | N/A |  | 5.6145 | 5.4 | 5.1913 | 4.6 | 4.7681 | 0.15909 | 0.52023 | 0
| 31 | No Data | N/A |  | 5.6145 | 5.4 | 5.1913 | 4.6 | 4.7681 | 0.15909 | 0.52023 | 0 | * Ignore zeros on charts for
| 32 | No Data | N/A |  | 5.6145 | 5.4 | 5.1913 | 4.6 | 4.7681 | 0.15909 | 0.52023 | 0 | test results without data.
| 33 | No Data | N/A |  | 5.6145 | 5.4 | 5.1913 | 4.6 | 4.7681 | 0.15909 | 0.52023 | 0
| 34 | No Data | N/A |  | 5.6145 | 5.4 | 5.1913 | 4.6 | 4.7681 | 0.15909 | 0.52023 | 0
| 35 | No Data | N/A |  | 5.6145 | 5.4 | 5.1913 | 4.6 | 4.7681 | 0.15909 | 0.52023 | 0
| 36 | No Data | N/A |  | 5.6145 | 5.4 | 5.1913 | 4.6 | 4.7681 | 0.15909 | 0.52023 | 0
| 37 | No Data | N/A |  | 5.6145 | 5.4 | 5.1913 | 4.6 | 4.7681 | 0.15909 | 0.52023 | 0
| 38 | No Data | N/A |  | 5.6145 | 5.4 | 5.1913 | 4.6 | 4.7681 | 0.15909 | 0.52023 | 0
| 39 | No Data | N/A |  | 5.6145 | 5.4 | 5.1913 | 4.6 | 4.7681 | 0.15909 | 0.52023 | 0
| 40 | No Data | N/A |  | 5.6145 | 5.4 | 5.1913 | 4.6 | 4.7681 | 0.15909 | 0.52023 | 0

## %Comp.
Tests for: |  | Density % |  | Test of: | [8 empty] | Cores
Test Method: |  | ATM 410 |  | Test Units: | [8 empty] | %
Chart by: |  | A.D. Charlie |  | Project #: | [8 empty] | 495Z7
Contractor: |  | Hi-Ball Construction |  | Item #: | [8 empty] | 401(1)
|  |  |  | Checked by: | [8 empty] | B. Johnson, P.A.
S. Date | Test No. | Test Result* | Range* | Notes | Test UCL | U. Spec | Test C/L | L. Spec. | Test LCL | Range C/L | Range UCL | Range LCL
2012-02-07 | 1 | 92.5 |  |  | 100 | 98 | 93.9542 | 92 | 87.8362 | 2.3 | 7.521 | 0 | Individual Tests | Chart data
2012-02-09 | 2 | 93.5 | 1 |  | 100 | 98 | 93.9542 | 92 | 87.8362 | 2.3 | 7.521 | 0 | Average (C/L) | 93.9542
2012-02-14 | 3 | 95.1 | 1.6 |  | 100 | 98 | 93.9542 | 92 | 87.8362 | 2.3 | 7.521 | 0
2012-02-19 | 4 | 89.3 | 5.8 |  | 100 | 98 | 93.9542 | 92 | 87.8362 | 2.3 | 7.521 | 0
2012-02-26 | 5 | 91.5 | 2.2 | Adj-4 | 100 | 98 | 93.9542 | 92 | 87.8362 | 2.3 | 7.521 | 0 | Upper Control Limit | 100
2012-02-27 | 6 | 88.6 | 2.9 | Adj-4 | 100 | 98 | 93.9542 | 92 | 87.8362 | 2.3 | 7.521 | 0 | Upper Spec. Limit | 98
2012-02-28 | 7 | 91.2 | 2.6 | Adj-4 | 100 | 98 | 93.9542 | 92 | 87.8362 | 2.3 | 7.521 | 0 | Lower Spec. Limit | 92
2012-02-29 | 8 | 93 | 1.8 |  | 100 | 98 | 93.9542 | 92 | 87.8362 | 2.3 | 7.521 | 0 | Lower Control Limit | 87.8362
2012-03-01 | 9 | 91.5 | 1.5 |  | 100 | 98 | 93.9542 | 92 | 87.8362 | 2.3 | 7.521 | 0
2012-03-04 | 10 | 93.1 | 1.6 |  | 100 | 98 | 93.9542 | 92 | 87.8362 | 2.3 | 7.521 | 0
2012-03-05 | 11 | 92 | 1.1 |  | 100 | 98 | 93.9542 | 92 | 87.8362 | 2.3 | 7.521 | 0
2012-03-06 | 12 | 96.5 | 4.5 |  | 100 | 98 | 93.9542 | 92 | 87.8362 | 2.3 | 7.521 | 0
2012-03-07 | 13 | 96.8 | 0.3 |  | 100 | 98 | 93.9542 | 92 | 87.8362 | 2.3 | 7.521 | 0
2012-03-08 | 14 | 96.8 | 0 |  | 100 | 98 | 93.9542 | 92 | 87.8362 | 2.3 | 7.521 | 0
2012-03-09 | 15 | 93.7 | 3.1 |  | 100 | 98 | 93.9542 | 92 | 87.8362 | 2.3 | 7.521 | 0
2012-03-11 | 16 | 96.5 | 2.8 |  | 100 | 98 | 93.9542 | 92 | 87.8362 | 2.3 | 7.521 | 0
2012-03-12 | 17 | 93 | 3.5 |  | 100 | 98 | 93.9542 | 92 | 87.8362 | 2.3 | 7.521 | 0
2012-03-13 | 18 | 94.8 | 1.8 |  | 100 | 98 | 93.9542 | 92 | 87.8362 | 2.3 | 7.521 | 0
2012-03-14 | 19 | 97.9 | 3.1 |  | 100 | 98 | 93.9542 | 92 | 87.8362 | 2.3 | 7.521 | 0
2012-03-15 | 20 | 94.7 | 3.2 |  | 100 | 98 | 93.9542 | 92 | 87.8362 | 2.3 | 7.521 | 0 | Test Ranges | Chart data
2012-03-16 | 21 | 95.7 | 1 |  | 100 | 98 | 93.9542 | 92 | 87.8362 | 2.3 | 7.521 | 0 | Average (C/L) | 2.3
2012-03-18 | 22 | 92.8 | 2.9 |  | 100 | 98 | 93.9542 | 92 | 87.8362 | 2.3 | 7.521 | 0
2012-03-19 | 23 | 97 | 4.2 |  | 100 | 98 | 93.9542 | 92 | 87.8362 | 2.3 | 7.521 | 0
2012-03-22 | 24 | 97.4 | 0.4 |  | 100 | 98 | 93.9542 | 92 | 87.8362 | 2.3 | 7.521 | 0 | Upper Control Limit | 7.521
| 25 | No Data | N/A |  | 100 | 98 | 93.9542 | 92 | 87.8362 | 2.3 | 7.521 | 0 | Lower Control Limit | 0
| 26 | No Data | N/A |  | 100 | 98 | 93.9542 | 92 | 87.8362 | 2.3 | 7.521 | 0
| 27 | No Data | N/A |  | 100 | 98 | 93.9542 | 92 | 87.8362 | 2.3 | 7.521 | 0
| 28 | No Data | N/A |  | 100 | 98 | 93.9542 | 92 | 87.8362 | 2.3 | 7.521 | 0
| 29 | No Data | N/A |  | 100 | 98 | 93.9542 | 92 | 87.8362 | 2.3 | 7.521 | 0
| 30 | No Data | N/A |  | 100 | 98 | 93.9542 | 92 | 87.8362 | 2.3 | 7.521 | 0 | * Ignore zeros on charts for
| 31 | No Data | N/A |  | 100 | 98 | 93.9542 | 92 | 87.8362 | 2.3 | 7.521 | 0 | test results without data.
| 32 | No Data | N/A |  | 100 | 98 | 93.9542 | 92 | 87.8362 | 2.3 | 7.521 | 0
| 33 | No Data | N/A |  | 100 | 98 | 93.9542 | 92 | 87.8362 | 2.3 | 7.521 | 0
| 34 | No Data | N/A |  | 100 | 98 | 93.9542 | 92 | 87.8362 | 2.3 | 7.521 | 0
| 35 | No Data | N/A |  | 100 | 98 | 93.9542 | 92 | 87.8362 | 2.3 | 7.521 | 0
| 36 | No Data | N/A |  | 100 | 98 | 93.9542 | 92 | 87.8362 | 2.3 | 7.521 | 0
| 37 | No Data | N/A |  | 100 | 98 | 93.9542 | 92 | 87.8362 | 2.3 | 7.521 | 0
| 38 | No Data | N/A |  | 100 | 98 | 93.9542 | 92 | 87.8362 | 2.3 | 7.521 | 0
| 39 | No Data | N/A |  | 100 | 98 | 93.9542 | 92 | 87.8362 | 2.3 | 7.521 | 0
| 40 | No Data | N/A |  | 100 | 98 | 93.9542 | 92 | 87.8362 | 2.3 | 7.521 | 0